## Gantt Chart
CAREERPATH AI: AN AI-BASED CAREER GUIDANCE SYSTEM PROVIDING CAREER DESCRIPTIONS AND JOB ROLE INSIGHTS FOR STUDENTS OF MERIDIAN EDUCATIONAL INSTITUTION INC.
CATEGORY | TASK | ASSIGNED TO | WEEK 1 (JULY 6-12) | WEEK 2 (JULY 13-19) | WEEK 3 (JULY 20-26) | WEEK 4 (JULY 27-AUGUST 2) | WEEK 5 (AUGUST 3-9) | WEEK 6 (AUGUST 10-16) | WEEK 7 (AUGUST 17-23) | WEEK 8 (AUGUST 24-30) | WEEK 9 (AUGUST 31-SEPTEMBER 6) | WEEK 10 (SEPTEMBER 7-13) | WEEK 11 (SEPTEMBER 14-20) | WEEK 12 (SEPTEMBER 21-27) | WEEK 13 (SEPTEMBER 28-OCTOBER 4) | WEEK 14 (OCTOBER 5-7)
SOFTWARE DEVELOPMENT
Build the responsive user interface (UI) for Students, Guidance Counselors, and Administrators
Develop user authentication (Login, Registration, Password Encryption, Session Management, RBAC)
Design and implement the MySQL database schema and relationships
Develop the Student Dashboard and Profile Management module
Build the RIASEC Career Assessment Questionnaire interface
Implement automatic RIASEC score computation based on assessment responses
Create the Career Database (RIASEC career profiles, descriptions, skills, and career pathways)
Develop the Python-based Career Recommendation Engine using Scikit-learn Cosine Similarity
Prepare and preprocess the career dataset for AI recommendation
Integrate the Python recommendation engine with PHP using an HTTP/REST API (cURL)
Display the Top 5 personalized career recommendations with similarity scores
Develop the Career Information page (career description, required skills, educational pathways, and job opportunities)
Develop the Guidance Counselor Dashboard (student monitoring, assessment records, recommendation results, consultation history, and analytics)
Implement Consultation Request and Appointment Scheduling between students and counselors
Develop the Notification Module for assessment results and consultation updates
Develop the Administrator Module (User Management, Career Management, Assessment Management, System Settings, Database Backup, and Audit Logs)
Generate downloadable assessment reports and career recommendation summaries (PDF/Print)
Integrate all system modules (Frontend + Backend + Database + AI Recommendation Engine)
Perform unit testing for all modules
Conduct integration testing and resolve system bugs
Optimize database queries, recommendation response time, and overall system performance
Conduct final system validation and prepare the deployment version for evaluation
Implement revisions and bug fixes based on adviser/client feedback
SYSTEM EVALUATION
Prepare the ISO/IEC 25010 evaluation questionnaire covering Functional Suitability, Performance Efficiency, Compatibility, Usability, Reliability, Security, Maintainability, and Portability
Validate the evaluation questionnaire with the research adviser
Coordinate the evaluation schedule with the Guidance Office and student respondents
Orient evaluators on the system's features and evaluation procedures
Conduct pilot testing of the evaluation instrument
Conduct system evaluation with IT experts
Conduct system evaluation with Guidance Counselors
Conduct system evaluation with student respondents
Collect completed evaluation questionnaires
Encode evaluation responses
Analyze evaluation results using descriptive statistics
Implement system improvements based on evaluator feedback
Perform final validation after revisions
RESEARCH PAPER WRITING
Revise Chapters 1–3 from future tense to past tense
Write Chapter 4: Presentation, Analysis, and Interpretation of Data (ISO/IEC 25010 Evaluation Results)
Write Chapter 5: Summary, Conclusions, and Recommendations
Update methodology based on the completed system implementation
Insert screenshots of the developed system and explain each module
Finalize tables, figures, and appendices
Update references and citations
Proofread and format the manuscript according to university guidelines
Submit the revised manuscript to the adviser for checking
Apply adviser corrections and finalize the thesis manuscript
Prepare PowerPoint presentation and defense materials
Print and submit the final manuscript and system requirements
CONSULTATION
Initial consultation to confirm project scope and development schedule
Review of Authentication and Student Module
Review of Guidance Counselor and Administrator Modules
Review of AI Career Recommendation Module
Review of integrated system and testing results
Review before system evaluation
Review after system evaluation and implementation of revisions
Final consultation before submission of requirements
Defense Preparation
| Prepare defense presentation slides | Rana
| Prepare a live system demo script and a backup video walkthrough | Parone
| Mock defense with the adviser | All
| Finalize System and Research Paper (check) | All